## User
NDS Unit Testing Status
USER
Login/Sign Up
User Story | Description | Validation | Test ID Group | Status
US01 | Account Sign Up | VA011 - Register Via Google Account | TS_LS_011
|  | VA012 - Password Format Validation | TS_LS_012
|  | VA013 - Account stored in Firebase | TS_LS_013
|  | VA014 - Registration Field Validation | TS_LS_014
|  | VA015 - Validation Email | TS_LS_015
|  | VA016 - DB Column creation for any user | TS_LS_016
US02 | Account Login | VA021 - Google Login Button | TS_LS_021
|  | VA022 - Validate if account exists | TS_LS_022
|  | VA024 - Refresh Webpage when logged in | TS_LS_024
US03 | Account Logout | VA031 - Logout Button | TS_LS_031
|  | VA032 - Automatic Logout | TS_LS_032
US04 | Reset Pasword | VA041 - Forgot Password Button | TS_LS_041
|  | VA042 - When selecting a correct email, a message is sent witha link to restore password. | TS_LS_042
|  | VA043 - Once clicked the pasword, the user should be sent to a page to define the new password. | TS_LS_043
|  | VA044 - Password Format Validation | TS_LS_044
|  | VA045- Update New Information | TS_LS_045
US10 | Search Without registration | VA101 - Only when the user clicks on a section/component that needs registering (buying a car, scheduling test drive and profile), the user will be sent to the register page. | TS_LS_101
US39 | Mobile Friendly | VA391 - All the sections mentioned in this flow (Account Sign Up Page, Login Page, Reset Password Page) need to adapt for phone users. | TS_LS_391
US44 | NL Search Always Available | VA441 - The search bar is visible even when the user scrolls down the page. | TS_LS_441
Completition %
Search Car
User Story | Description | Validation | Unit Testing | Status
US39 | Mobile Friendly | VA391 - All the sections mentioned in this flow (Account Sign Up Page, Login Page, Reset Password Page) need to adapt for phone users. | TS_SC_391
US40 | Allow the user to search for a car without any technical description | VA401 - Landing Page Search Barch | TS_SC_401
|  | VA402 - The application must have NL model that allows to interpret the input of user and send the request to DB. | TS_SC_402
|  | VA403 - Filter Cars | TS_SC_403
|  | VA404 - NL token accuracy | TS_SC_404
US43 | No login Search | VA431 - Users without login in are able to search cars with NL function | TS_SC_431
|  | VA432 - User without login ara able to search cars with form search | TS_SC_432
|  | VA433 - User without login are able to serach cars with filter function | TS_SC_433
US61 | Home Page | VA611 - Easy access Search Bar | TS_SC_611
|  | VA612 - Easy access purchase button | TS_SC_612
|  | VA613 - Test Drive Button | TS_SC_613
Completition %
Car Details
User Story | Description | Validation | Unit Testing | Status
US13 | Payment Opportunities | VA131 - For each car details, ther most be the financial option available | TS_CD_131
|  | VA132 - The user can modify the various options for the selected car | TS_CD_132
US14 | Payment Custom Order | VA141 - Show customization for a specific car | TS_CD_141
|  | VA142 - Remove option to select customization if it is not currently available | TS_CD_142
|  | VA143 - There must be a customize button on the cars that offer this option. | TS_CD_143
US15 | Download Quotes | VA151 - Display the "download" button near the displayed price of the car | TS_CD_151
|  | VA152 - The quote is downloaded in the client's browser | TS_CD_152
US39 | Mobile Friendly | VA391 - All the sections mentioned in this flow (Account Sign Up Page, Login Page, Reset Password Page) need to adapt for phone users. | TS_CD_391
US45 | Car Visualization | VA451 - For every car that is displayed, it must have general information before clicking the car for more details. | TS_CD_451
|  | VA452 - If the user selects a specific car, they will be redirected to another section with all the description of the car. | TS_CD_452
US47 | Indoor and outoor display | VA471 - When the user selects a vehicle, they can go through the images provided by the car dealerships, to explore its structure both inside and outside in detail. | TS_CD_471
|  | VA472 - Inside the car details, the users will be able to view the vehicle 360º. | TS_CD_472
Completition %
Edit Profile
User Story | Description | Validation | Unit Testing | Status
US09 | Delete account | VA091 - Display message that informs the user how to delete their account (via email). | TS_EP_091
|  | VA092 - Delete the user information from DB and Firebase. | TS_EP_092
US38 | Modify personal information | VA381 - When a registered user clicks the edit button, changes a field and saves the data, it is stored in Firebase and the old information is erased. | TS_EP_381
US39 | Website access | VA391 - User can enter the web page in any device with internet connection | TS_EP_391
Completition %
Place Car Order
User Story | Description | Validation | Unit Testing | Status
US11 | US11 - User payment information registration | VA111 - Be able to select from a variety of payment methods (Credit Card, Dealership bank information, etc...) | TS_PO_111
|  | VA112 - Submit personal information in order to make the payment. | TS_PO_112
|  | VA113 - A stripe component will be rendered to make the payment (if stripe is chosen as the payment method). | TS_PO_113
|  | VA114 - If successful, add transaction information (Ej.- payment history) to the database. If an error occurs, show it to the user. | TS_PO_114
US18 | Dynamic Pricing | VA181 - Reflect changes on the final price when selecting extras, such as car customizations and financing/insurance options. | TS_PO_181
US24 | Secure Payments | VA241 The user will be able to perform a transaction with the certantty that the money will be correctly sent to the destintation without any probability of lost. | TS_PO_241
US39 | Website access | VA391 - User can enter the web page in any device with internet connection | TS_PO_391
US41 | Displaying the available financing plans submitted by the car retailer | VA411 -A list of different insurance options with the price of each of the options will be displayed in the car details page.r various questions regarding the car being looked. | TS_PO_411
|  | VA412 - A list of different financing options with the price of each of the options will be displayed in the car details page. | TS_PO_412
Completition %
Communication
User Story | Description | Validation | Unit Testing | Status
US19 | Account actions notifications | VA191 When a change operation is made within the account send notification (email and/or sms). | TS_CM_191
|  | VA192 When requesting a driving test send notification (email and/or sms). | TS_CM_192
|  | VA193 When requesting a quote send notification (email and/or sms). | TS_CM_193
|  | VA194 When trying to purchase a vehicle send a notification (email and/or sms). | TS_CM_194
|  | VA195 Confirm a vehicle purchase and have confirmation sent to the email. | TS_CM_195
|  | VA196 - Notification when car agency approves Test Drive | TS_CM_196
|  | VA197 - Send notification when a chat message is received | TS_CM_197
|  | VA198 - Miscellaneous notifications | TS_CM_198
US27 | Users Re-engagement | VA271 After 2 weeks from inactivity, the system will send them a email inviting them to check the new deals and cars at MOVU. | TS_CM_271
US37 | Car status | VA371 - User can keep track of their purchase status when entering a specific car in their list. | TS_CM_371
|  | VA372 - Car Status (Payment and Delivery) View | TS_CM_372
US39 | Website access | VA391 - User can enter the web page in any device with internet connection | TS_CM_391
US50 | Chat with Vendor | VA501 - User should be able to begin a conversation with their vendor | TS_CM_501
US51 | Chat with Chatbot | VA511 - At all times, the user can quickly begin a conversation with our chatbot, which will give the user the various questions that it can respond to | TS_CM_511
US52 | Email Notifications | VA521 Whenever an update on the users car purchase progress is done, they should be able to receive an email detailing the current status | TS_CM_521
Completition %
Wishlist
User Story | Description | Validation | Unit Testing | Status
US39 | Website access | VA391 - User can enter the web page in any device with internet connection | TS_WL_391
US46 | Car characteristics comparison | VA461 - While inspecting the vehicles, the user will be able to click a button that redirects them to a comparative section. | TS_WL_461
|  | VA462 - The webpage will give the user the list of all available cars, in which they can select two cars to compare | TS_WL_462
|  | VA463 - Once the cars are selected, the key car characteristics will be placed side by side for better analysis. | TS_WL_463
US49 | Car shopping Wishlist | VA491 - When looking for a car there is going to be a "wish list" button next to each car (both in card and description mode) where the user can add cars to a wish list page. | TS_WL_491
|  | VA492 - When accessing the wishlist, all the cars previously select need to appear in this section. | TS_WL_492
Completition %
Car Test Registration
User Story | Description | Validation | Unit Testing | Status
US39 | Website access | VA391 - User can enter the web page in any device with internet connection | TS_CTR_391
US56 | Test Drive Requirements | VA561 - Salesman Dashboard will be a section to manage the test drives. Here the salesman can view the applications as well as approving or denying the test | TS_CTR_561
US57 | Skip Drive | VA571 - Making sure the Test Drive is not a requirement to purchase the vehicle | TS_CTR_571
US59 | Filter of Cars applicable for Test Drive | VA591 - When a vehicle is uploaded to the platform, there is a box, "available for a test drive", when selected it is added to your inventory for test drive requests, customers can see which vehicle they can request at the selected agency (management view) | TS_CTR_591
Completition %

## LS
Project | NDS MOVU
Flow | User Login/Sign Up (LS)
QA Lead | Salvador Salgado Normandia
Tester | -
History User Id | History User | Test Id | Test Case | Test description | Steps | Test data | Expected | Result | Status | Execution date | Executed by | Comments
US01 | Account Sign Up | TS_LG_SIGNUP_011_1 | Register Via Google Account | Click on Google signup button and be redirected | 1. Go to Login Page 2. Click on Google Button 3. Be redirected to Google Sign In page | OnClick() in component | User should be redirected to Google sign in webpage |  | Pending
US01 | Account Sign Up | TS_LG_SIGNUP_011_2 | Register Via Google Account | Click on Google signup button and be redirected | 1. Go to Login Page 2. Click on Google Button 3. Be redirected to Google Sign In page | OnClick() in component | User should be redirected to Google sign in webpage |  | In Proccess
US01 | Account Sign Up | TS_LG_SIGNUP_02_1 | Search Bar no results | Enter a text with no results | 1. Go search page 2. Enter text | "MG" | No results in page with a message "No results" |  | Pending
US01 | Account Sign Up | TS_LG_SIGNUP_03_1 | Search Bar invalid | Enter an invalid text | 1. Go search page 2. Enter text | "Bike" | No results in page with a message "Invalid search" |  | In Proccess
US01 | Account Sign Up | TS_LG_012_1 | [6 empty] | In Proccess
US01 | Account Sign Up | TS_LG_013_1 | [6 empty] | In Proccess
US01 | Account Sign Up | TS_LG_SIGNUP_014_1 | [6 empty] | In Proccess
US01 | Account Sign Up | TS_LG_SIGNUP_015_1 | [6 empty] | In Proccess
US02 | Account Login | TS_LS_021_1 | [6 empty] | In Proccess

## SC
Project | NDS MOVU
Flow | Search Car (SC)
QA Lead | Salvador Salgado Normandia
Tester | -
History User Id | History User | Test Id | Test Case | Test description | Steps | Test data | Expected | Result | Status | Execution date | Executed by | Comments
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
In Proccess
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending
Pending

## CD
Project | NDS MOVU
Flow | Car Details (CD)
QA Lead | Salvador Salgado Normandia
Tester | -
History User Id | History User | Test Id | Test Case | Test description | Steps | Test data | Expected | Result | Status | Execution date | Executed by | Comments

## EP
Project | NDS MOVU
Flow | Edit Profile (EP)
QA Lead | Salvador Salgado Normandia
Tester | -
History User Id | History User | Test Id | Test Case | Test description | Steps | Test data | Expected | Result | Status | Execution date | Executed by | Comments

## PO
Project | NDS MOVU
Flow | Place Car Order (PO)
QA Lead | Salvador Salgado Normandia
Tester | -
History User Id | History User | Test Id | Test Case | Test description | Steps | Test data | Expected | Result | Status | Execution date | Executed by | Comments

## CM
Project | NDS MOVU
Flow | Communication (CM)
QA Lead | Salvador Salgado Normandia
Tester | -
History User Id | History User | Test Id | Test Case | Test description | Steps | Test data | Expected | Result | Status | Execution date | Executed by | Comments

## WL
Project | NDS MOVU
Flow | Wishlist (WL)
QA Lead | Salvador Salgado Normandia
Tester | -
History User Id | History User | Test Id | Test Case | Test description | Steps | Test data | Expected | Result | Status | Execution date | Executed by | Comments

## CTR
Project | NDS MOVU
Flow | Car Test Registration (CTR)
QA Lead | Salvador Salgado Normandia
Tester | -
History User Id | History User | Test Id | Test Case | Test description | Steps | Test data | Expected | Result | Status | Execution date | Executed by | Comments

## Salesman
NDS Unit Testing Status
Salesman
Chat Management
User Story | Description | Validation | Unit Testing | Start Date | End Date | Status
US53 | Chats Managements | VA531 In the Vendor Dashboard, the vendors will be able to visualize all the conversations with their clients
US54 | Chats Recordings | VA541 Once either a chat conversation or vendor chat has been concluded, it will be stored for both customer support review as well as any misuse of the tool
Clients Management
User Story | Description | Validation | Unit Testing | Start Date | End Date | Status
US35 | Sells status | VA351 - Sale status table for each salesma
US36 | Current Status on Car Purchases | VA361 - Salesman display of car purchase with its respective information
VA362 - Salesman can change the status of the car and it will show on the buyers car purchase
Vendor Insight
User Story | Description | Validation | Unit Testing | Start Date | End Date | Status
US34 | Data Visualization Vendor | VA341 - Salesman table of clients where they can check each clients information
VA342 - Salesman charts with their work development information

## Car Dealership
NDS Unit Testing Status
Car Dealership
Payments Management
User Story | Description | Validation | Unit Testing | Start Date | End Date | Status
US20 | Login / Sign Up | VA202 - In case the access credentials are not valid, the system will not allow the user to access the account and will show an error message.
US12 | Register car dealership payment information | VA121 - Car dealership submits bank account details to Stripe.
VA122 - Save encrypted data in Stripe.
US16 | Setting up financing plans | VA161 - When a manager uploads a car, he will need to fill out a cost section where he can add fixed options that his car dealership has available, such as the different insurance plans, and financing options so that platform users can view them in their quotes.
VA162 - A submit button that will upload to the cars page the financing and insurance options.
Car Dealership Management
User Story | Description | Validation | Unit Testing | Start Date | End Date | Status
US30 | Authorization in Procedures | VA301 In some specific steps during the car purchase process, in order to continue with the next steps it will be required that the manager approves the completion of the current one.
VA302 If there is no approval from manager or seller, the car purchase will not be able to continue
US31 | Vendors Administration | VA311 - Create an employee account
VA312 - Update employee account
VA313 - Get employee accounts from an automotive group
VA314 - Delete employee account
US33 | US33- Car Dealership Catalog | VA331 - Catalogue in web page
VA332 - Create new car in catalogue
VA333 - Update car in vehicle catalogue
VA334 - Remove car from catalogue
VA335 - Upload cars by a csv file
VA336 - Salesman can view the cars that are in their charge
US58 | Test Drive Documents | VA581 - When requesting a test drive the user should have an input to upload multiple files
VA582 - Have as a mandatory requirement the submission of all necessary documents
US32 | Data Visualization MG | VA321 - Summary of vendor sales table
VA322 - Top Sales Chart
VA323 - Car Visualization Table

## Automotive Group
NDS Unit Testing Status
Automotive Group
AG Management
User Story | Description | Validation | Unit Testing | Start Date | End Date | Status
US17 | Car dealership register | VA171 - Form where automotive group manager can input the necessary information in order to submit the car dealership application. | TS_AMG_171
|  | VA172 - The automotive group administrator lands on the application page where they can submit the documents to register the car dealership and wait for the super admin to validate. | TS_AMG_172
|  | VA173 - If the super admin changes the status, the car dealership can see the comments made and the status of the application. | TS_AMG_173
|  | VA174 - When the status of application is accepted the car dealership gains access the car dealership administration web page sections. | TS_AMG_174
US60 | User Documentation Definitions | VA601 - In the admin dashboard there will be an option to define which documents are required for every step during the purchasing process | TS_AMG_601
US29 | Data Visualization AD | VA291 In the Admin Dashboard, the user will be able to visualize a data summary of all the agencies owned (number of sales per agency, most sold cars, etc) | TS_AMG_291

## AMG
Project | NDS MOVU
Flow | AG Management (AMG)
QA Lead | Salvador Salgado Normandia
Tester | -
History User Id | History User | Test Id | Test Case | Test description | Steps | Test data | Expected | Result | Status | Execution date | Executed by | Comments
US17 | Car dealership register | TS_AMG_171 | VA171 - Form where automotive group manager can input the necessary information in order to submit the car dealership application. | [5 empty] | Pending
US17 | Car dealership register | TS_AMG_172 | VA172 - The automotive group administrator lands on the application page where they can submit the documents to register the car dealership and wait for the super admin to validate. | [5 empty] | Pending
US17 | Car dealership register | TS_AMG_173 | VA173 - If the super admin changes the status, the car dealership can see the comments made and the status of the application. | [5 empty] | Pending
US17 | Car dealership register | TS_AMG_174 | VA174 - When the status of application is accepted the car dealership gains access the car dealership administration web page sections. | [5 empty] | Pending
US60 | User Documentation Definitions | TS_AMG_601 | VA601 - In the admin dashboard there will be an option to define which documents are required for every step during the purchasing process | [5 empty] | Pending
US29 | Data Visualization AD | TS_AMG_291 | VA291 In the Admin Dashboard, the user will be able to visualize a data summary of all the agencies owned (number of sales per agency, most sold cars, etc) | [5 empty] | Pending

## SuperAdmin
NDS Unit Testing Status
Super Admin
SA Management
User Story | Description | Validation | Unit Testing | Start Date | End Date | Status
US05 | Super admin register | VA051 - The super admin can register into the platform by email or a Google account. | TS_SMG_051
|  | VA052 - The super admin must have a secure password with at least 8 characters. | TS_SMG_052
|  | VA053 - The email and password must be stored in firebase. | TS_SMG_053
|  | VA054 - If at least one field is not valid, the user can not continue registering. | TS_SMG_054
US06 | Manage automotive group sign up requests | VA061 - Table with all the applications of the automotive groups. | TS_SMG_061
|  | VA062 - Super Admin can change the status of application from "En revisión" to "Activa" or "Inactiva". | TS_SMG_062
|  | VA063 - Super Admin can check the information (submission documents) the automotive group send to validate. | TS_SMG_063
|  | VA064 - Super Admin can check a list of all the automitive groups with their data, including the dealership list for each group | TS_SMG_064
US62 | Automotive Groups Documentation Application Approvals | VA621 - In the super admin Dashboard, the super admin will have a section in which they can validate or reject new Automotive Groups Applications | TS_SMG_621
US21 | Roles/Permissions Configurations | VA212 - When a user is denied access to a specific action, the system will display an unathenticated message in the appropiate page. | TS_SMG_211
US25 | Data Privacy | VA251 - Each user will have their corresponding roles assigned that will grant them specific actions | TS_SMG_251
US26 | Data Visualization SAD | VA261 - In the Super Admin Dashboard, there will be a section which contains some data Summaries from all the car dealerships. | TS_SMG_261
US28 | Commissions | VA281 - For every cas uploaded to the system, be from catalog upload or individual, a percentage of a the car price should be given to NDS as part of comission. | TS_SMG_281

## SMG
Project | NDS MOVU
Flow | SA Management (SMG)
QA Lead | Salvador Salgado Normandia |  |  |  | Ingreso minimo de 5,000 | Happy weekend | Karina Puebla
Tester | - |  |  |  | 10,000-15,000
History User Id | History User | Test Id | Test Case | Test description | Steps | Test data | Expected | Result | Status | Execution date | Executed by | Comments
US05 | Super admin register | TS_SMG_051 | VA051 - The super admin can register into the platform by email or a Google account. | Click on Google signup button and be redirected | 1. Go to Login Page 2. Click on Google Button 3. Be redirected to Google Sign In page | OnClick() in component | User should be redirected to Google sign in webpage |  | Pending
US05 | Super admin register | TS_SMG_052 | VA052 - The super admin must have a secure password with at least 8 characters. | Check password field doesn't allow text with less than 8 characters | 1. Insert 7 chracter password 2. Click in register button. | OnClick() in component |  |  | Pending
US05 | Super admin register | TS_SMG_053 | VA053 - The email and password must be stored in firebase. | [5 empty] | Pending
US05 | Super admin register | TS_SMG_054 | VA054 - If at least one field is not valid, the user can not continue registering. | [5 empty] | Pending
US06 | Manage automotive group sign up requests | TS_SMG_061 | VA061 - Table with all the applications of the automotive groups. | [5 empty] | Pending
US06 | Manage automotive group sign up requests | TS_SMG_062 | VA062 - Super Admin can change the status of application from "En revisión" to "Activa" or "Inactiva". | [5 empty] | Pending
US06 | Manage automotive group sign up requests | TS_SMG_063 | VA063 - Super Admin can check the information (submission documents) the automotive group send to validate. | [5 empty] | Pending
US06 | Manage automotive group sign up requests | TS_SMG_064 | VA064 - Super Admin can check a list of all the automitive groups with their data, including the dealership list for each group | [5 empty] | Pending
US62 | Automotive Groups Documentation Application Approvals | TS_SMG_621 | VA621 - In the super admin Dashboard, the super admin will have a section in which they can validate or reject new Automotive Groups Applications | [5 empty] | Pending
US21 | Roles/Permissions Configurations | TS_SMG_211 | VA212 - When a user is denied access to a specific action, the system will display an unathenticated message in the appropiate page. | [5 empty] | Pending
US25 | Data Privacy | TS_SMG_251 | VA251 - Each user will have their corresponding roles assigned that will grant them specific actions | [5 empty] | Pending
US26 | Data Visualization SAD | TS_SMG_261 | VA261 - In the Super Admin Dashboard, there will be a section which contains some data Summaries from all the car dealerships. | [5 empty] | Pending
US28 | Commissions | TS_SMG_281 | VA281 - For every cas uploaded to the system, be from catalog upload or individual, a percentage of a the car price should be given to NDS as part of comission. | [5 empty] | Pending